## Story1
[11 empty] | Interval: | Start On: | End on | Days | Days left | Tasks/Day | Target | No | Unit | Days | Interval
[11 empty] | 1 | 2019-03-03 | 2019-03-15 | 13 | 3 | 3.3846 | 33.8462 | 1 | weekend | 2 | 0.16667
[11 empty] | Today: | 2019-03-12 06:51 | [5 empty] | 1 | week | 4.9 | 0.40833
[10 empty] | No | Date | Target | Actual | Work | Accum | Todo |  | 2 | weeks | 11.8 | 0.98333
[10 empty] | 0 | 2019-03-03 | 44 | 44 |  |  | 0 |  | 3 | weeks | 18.7 | 1.5583
[10 empty] | 1 | 2019-03-04 |  | 44 | 0 | 0 | 3.6667 |  | 4 | weeks | 25.6 | 2.1333
[10 empty] | 2 | 2019-03-05 |  | 42 | 2 | 2 | 7.3333
[10 empty] | 3 | 2019-03-06 |  | 42 | 0 | 2 | 11
[10 empty] | 4 | 2019-03-07 |  | 42 | 0 | 2 | 14.6667
[10 empty] | 5 | 2019-03-08 |  | 42 | 0 | 2 | 18.3333
[10 empty] | 6 | 2019-03-09 |  | 42 | 0 | 2 | 22
[10 empty] | 7 | 2019-03-10 |  | 42 | 0 | 2 | 25.6667
[10 empty] | 8 | 2019-03-11 |  | 42 | 0 | 2 | 29.3333
[10 empty] | 9 | 2019-03-12 |  | 42 | 0 | 2 | 33
[10 empty] | 10 | 2019-03-13 |  | 42 | 0 | 2 | 36.6667
[10 empty] | 11 | 2019-03-14 |  | 42 | 0 | 2 | 40.3333
[10 empty] | 12 | 2019-03-15 | 0 | 42 | 0 | 2 | 44
Story1:Todo
| No | Task | Asigned | Done | Tested | Verified
| 1 | Blackbook design | x | x | na | na
| 2 | Excel design | na | na | na | na
| 3 | Define name |  |  | na | na
| 4 | Create Repo |  |  | na | na
| 5 | Setup Readme |  |  | na | na
| 6 | Setup environment
| 7 | Setup build
| 8 | Define scope |  |  | na | na
| 9 | Dev1
| 10 | Dev2
| 11 | Dev3
| 12 | Test
| 13 | Build
| 14 | Publish |  |  | na | na
| 15 | QA
|  | (na) | 1 | 1 | 7 | 7 | Done | Todo | Progress
Story1:Todo |  | 15 | 1 | 1 | 0 | 0 | 2 | 44 | 4.545%
Formulas:
Days = DATEDIF([Start On:],[End on],"d")+1
Days left = DATEDIF([Start On:, row below],[End on],"d")
Note on M1: 1 weekend = 0.17 1 week = .41 2 weeks = .98 3 weeks = 1.56 4 weeks = 2.13

## Create Repo
ü | (New Project)
[[Create repo]]
[Define name]
[Setup Github]
[Setup WhiteSource]
[Clone repo]
[[Setup readme]]
[edit readme]
[ll badges readme]
[ll readme usage]
[MIT license]
[[Setup environment]]
[copy sid_clone.bat]
[edit folder & run]
[yarn]
[edit package.json]
[npm test]
[npm run rules]
[initial commit]
[[setup build]]
[setup travis]
[setup codefactor]
[QA]
(end)

## Development
ü | (Develop module)
[[Define scope]]
Test
Build
Publish
QA