## Story1
[12 empty] | Interval: | Start On: | End on | Days | Days left | Tasks/Day | Target | No | Unit | Days | Interval
[12 empty] | 0.17 | 2019-03-08 | 2019-03-10 00:58 | 3 | 0 | 23 | 0 | 1 | weekend | 2 | 0.16667
[12 empty] | Today: | 2019-03-10 17:04 | [5 empty] | 1 | week | 4.9 | 0.40833
[11 empty] | No | Date | Target | Actual | Work | Accum | Todo |  | 2 | weeks | 11.8 | 0.98333
[11 empty] | 0 | 2019-03-08 | 69 | 69 |  |  | 0 |  | 3 | weeks | 18.7 | 1.5583
[11 empty] | 0.17 | 2019-03-08 04:05 |  | 69 | 0 | 0 | 0.9775 |  | 4 | weeks | 25.6 | 2.1333
[11 empty] | 0.34 | 2019-03-08 08:10 |  | 57 | 12 | 12 | 1.955
[11 empty] | 0.51 | 2019-03-08 12:14 |  | 42 | 27 | 27 | 2.9325
[11 empty] | 0.68 | 2019-03-08 16:19 |  | 40 | 29 | 29 | 3.91
[11 empty] | 0.85 | 2019-03-08 20:24 |  | 37 | 32 | 32 | 4.8875
[11 empty] | 1.02 | 2019-03-09 00:29 |  | 37 | 0 | 32 | 5.865
[11 empty] | 1.19 | 2019-03-09 04:34 |  | 37 | 0 | 32 | 6.8425
[11 empty] | 1.36 | 2019-03-09 08:38 |  | 37 | 0 | 32 | 7.82
[11 empty] | 1.53 | 2019-03-09 12:43 |  | 37 | 32 | 32 | 8.7975
[11 empty] | 1.7 | 2019-03-09 16:48 |  | 37 | 32 | 32 | 9.775
[11 empty] | 1.87 | 2019-03-09 20:53 |  | 9 | 60 | 60 | 10.7525
[11 empty] | 2.04 | 2019-03-10 00:58 | 0 | 0 | 69 | 69 | 11.73
Story1:Todo
| No | Task | Asigned | Done | Tested | Verified
| 1 | Blackbook design | x | x | na | na
| 2 | Excel design | na | na | na | na
| 3 | Define name | x | x | na | na
| 4 | Create Repo | x | x | na | na
| 5 | Setup Readme | x | x | na | na
| 6 | Setup environment | x | x | x | x
| 7 | Setup build | x | x | x | x
| 8 | Define scope | x | x | na | na
| 9 | Create console app flowedit | x | x | x | x
| 10 | add options | x | x | x | x
| 11 | -f option mockup | x | x | x | x
| 12 | -o option mockup | x | x | x | x
| 13 | -s option mockup | x | x | x | x
| 14 | -d option mockup | x | x | x | na
| 15 | build test cases (webstorm) | x | x | x | na
| 16 | Test | x | x | x | x
| 17 | Build final app (timer) | x | x | x | na
| 18 | WebStorm | x | x | x | x
| 19 | MS code | x | x | x | x
| 18 | Publish | x | x | na | na
| 19 | QA | x | x | na | na
| 20 | Refactor helper | x | x | x | x
| 21 | Update see_it_done project | x | x | na | na
|  | (na) | 1 | 1 | 9 | 12 | Done | Total | Todo | Progress
Story1:Todo |  | 23 | 22 | 22 | 14 | 11 | 69 | 69 | 0 | 100%
Formulas:
Days = DATEDIF([Start On:],[End on],"d")+1
Days left = DATEDIF([Start On:, row below],[End on],"d")
Note on N1: 1 weekend = 0.17 1 week = .41 2 weeks = .98 3 weeks = 1.56 4 weeks = 2.13

## Backlog
ü | (New Idea)
[[Create backlog]]
[I want to...]
<Can I …?> [so that] ?? (end)
[Write stories]
[Write notes]
[review stories]
[Log stories]
[Create burndown chart]
[kickoff]
(end)

## Create Repo
ü | (New Project)
[[Create repo]]
[Define name]
[Setup Github]
[Setup WhiteSource]
[Clone repo]
[[Setup readme]]
[edit readme]
[ll badges readme]
[ll readme usage]
[MIT license]
[[Setup environment]]
[copy sid_clone.bat]
[edit folder & run]
[yarn]
[edit package.json]
[npm test]
[npm run rules]
[initial commit]
[[setup build]]
[setup travis]
[setup codefactor]
[QA]
(end)

## Development
ü | (Develop module)
[[Define scope]]
Test
Build
Publish
QA