## Sprint1
| Philosophy: The duration of individual tasks does not matter. What really matter is that everything shall to be done on or before the deadline! | [10 empty] | Duration Factor | [5 empty] | Target Tasks | Contingency days |  | 0.1 | Duration Factor | Days
[13 empty] | Start On: | End on | Days | Days left | Tasks/Day |  | Count | Unit | Days |  | Work | Full
[12 empty] | 1.15 | 2019-10-23 | 2019-11-05 19:12 | 14 | 13 | 3.3571 | 3.3571 | 1 | weekend | 2 | 0.16667 |  | 2
[12 empty] | Today: | 2019-10-23 09:24 | [5 empty] | 1 | week | 6.9 | 0.575 | 5 | 7
[10 empty] | No | Interval | Date | Target | Actual | Done | Acumu-lative | Todo |  | 2 | weeks | 13.8 | 1.15 | 10 | 14
[11 empty] | 0 | 2019-10-23 | 47 | 47 |  |  |  |  | 3 | weeks | 20.7 | 1.725 | 15 | 21
[10 empty] | 1 | 1.15 | 2019-10-24 03:36 |  | 45 | 2 | 2 | 4.5042 |  | 4 | weeks | 27.6 | 2.3 | 20 | 28
[10 empty] | 2 | 2.3 | 2019-10-25 07:12 |  | 43 | 4 | 4 | 9.0083 |  | 5 | weeks | 34.5 | 2.875 | 25 | 35
[10 empty] | 3 | 3.45 | 2019-10-26 10:48 |  | 41 | 6 | 6 | 13.5125 |  | 6 | weeks | 41.4 | 3.45 | 30 | 42
[10 empty] | 4 | 4.6 | 2019-10-27 14:24 |  | 41 | 0 | 6 | 18.0167 |  | 7 | weeks | 48.3 | 4.025 | 35 | 49
[10 empty] | 5 | 5.75 | 2019-10-28 18:00 |  | 41 | 0 | 6 | 22.5208 |  | 8 | weeks | 55.2 | 4.6 | 40 | 56
[10 empty] | 6 | 6.9 | 2019-10-29 21:36 |  | 41 | 0 | 6 | 27.025
[10 empty] | 7 | 8.05 | 2019-10-31 01:12 |  | 41 | 0 | 6 | 31.5292
[10 empty] | 8 | 9.2 | 2019-11-01 04:48 |  | 41 | 0 | 6 | 36.0333
[10 empty] | 9 | 10.35 | 2019-11-02 08:24 |  | 41 | 0 | 6 | 40.5375
[10 empty] | 10 | 11.5 | 2019-11-03 12:00 |  | 41 | 0 | 6 | 45.0417
[10 empty] | 11 | 12.65 | 2019-11-04 15:36 |  | 41 | 0 | 6 | 49.5458
[10 empty] | 12 | 13.8 | 2019-11-05 19:12 | 0 | 41 | 0 | 6 | 54.05
Sprint story:What? Why? For Who?
| No | Task | Asigned | Done | Verified | Presented
| 1 | Research context | x |  | na | na
| 2 | Terms & Accronyms | x |  | na | na
| 3 | Mindmap design |  |  |  | na
| 4 | Quotes (costs / times)
| 5 | Cost Analysis
| 6 | Risk Register
| 7 | Presentation
| 8 | Approval
| 9 | Task3
| 10 | Task4
| 11 | Task5
| 12 | Task6
| 13 | Task7
| 14 | QA
| 15 | Close-out
|  |  |  | (na) | 2 | 3 | Done | Todo | Progress
Totals |  | 13 | 2 | 0 | 0 | 0 | 2 | 47 | 4.255%
Formulas:
Days = DATEDIF([Start On:],[End on],"d")+1
Days left = DATEDIF([Start On:, row below],[End on],"d")
Adding tasks:
(More tasks can be added easily)
1. Insert spreadsheet lines
2. Drag table bigger
Sprint always has 12 status update events
Total Time to complete sprint:
- Contingency is subtracted from time
- Contigency of 2 days will exclude weekends
- Contigency of 0.1 days is about 2.4 hours / 24 hour day
(Real time is used -> 24 hour days & 7 days / week)
Format Dates:
dd-mmm (hh:mm)
dd-mmm
Note on X2: Days per week Default is 0.1 (2.4 hours per day or 17 hours per week)
Note on Y2: Duration factor is used to set the interval time for status updates for the sprint. (There is always 12 status updates)
Note on N4: See Duration Factor table
Note on O4: Add sprint start date
Note on C23: Every tasks has 4 stages before completion. Add "x" when task is completed.
Note on D23: Task is assigned to someone and has started
Note on E23: Task is reported to be completed
Note on F23: Task was verified by 2nd party. Mark with "x" if completed. Mark with "na" if task is not verified.
Note on G23: Task was presented to stakeholders. Mark with "x" if completed. Mark with "na" if task is not presented.
Note on F41: Verified "na" total
Note on G41: Presented "na" total
Note on C42: Total Tasks
Note on D42: Total assigned
Note on E42: Total done
Note on F42: Total verified
Note on G42: Total presented

## Sprint2
Copy Sprint 1 to this tab and update values to capture next sprint.