## Sprint1
| Philosophy: The duration of individual tasks does not matter. What really matter is that everything shall to be done on or before the deadline! | [10 empty] | Duration Factor | [5 empty] | Target Tasks | Contingency days |  | 0.1 | Duration Factor | Days
[13 empty] | Start On: | End on | Days | Days left | Tasks/Day |  | Count | Unit | Days |  | Work | Full
[12 empty] | 1.15 | 2019-10-23 | 2019-11-05 19:12 | 14 | 13 | 3.3571 | 3.3571 | 1 | weekend | 2 | 0.16667 |  | 2
[12 empty] | Today: | 2019-10-23 09:53 | [5 empty] | 1 | week | 6.9 | 0.575 | 5 | 7
[10 empty] | No | Interval | Date | Target | Actual | Done | Acumu-lative | Todo |  | 2 | weeks | 13.8 | 1.15 | 10 | 14
[11 empty] | 0 | 2019-10-23 | 47 | 47 |  |  |  |  | 3 | weeks | 20.7 | 1.725 | 15 | 21
[10 empty] | 1 | 1.15 | 2019-10-24 03:36 |  | 45 | 2 | 2 | 4.5042 |  | 4 | weeks | 27.6 | 2.3 | 20 | 28
[10 empty] | 2 | 2.3 | 2019-10-25 07:12 |  | 43 | 4 | 4 | 9.0083 |  | 5 | weeks | 34.5 | 2.875 | 25 | 35
[10 empty] | 3 | 3.45 | 2019-10-26 10:48 |  | 41 | 6 | 6 | 13.5125 |  | 6 | weeks | 41.4 | 3.45 | 30 | 42
[10 empty] | 4 | 4.6 | 2019-10-27 14:24 |  | 41 | 0 | 6 | 18.0167 |  | 7 | weeks | 48.3 | 4.025 | 35 | 49
[10 empty] | 5 | 5.75 | 2019-10-28 18:00 |  | 41 | 0 | 6 | 22.5208 |  | 8 | weeks | 55.2 | 4.6 | 40 | 56
[10 empty] | 6 | 6.9 | 2019-10-29 21:36 |  | 41 | 0 | 6 | 27.025
[10 empty] | 7 | 8.05 | 2019-10-31 01:12 |  | 41 | 0 | 6 | 31.5292
[10 empty] | 8 | 9.2 | 2019-11-01 04:48 |  | 41 | 0 | 6 | 36.0333
[10 empty] | 9 | 10.35 | 2019-11-02 08:24 |  | 41 | 0 | 6 | 40.5375
[10 empty] | 10 | 11.5 | 2019-11-03 12:00 |  | 41 | 0 | 6 | 45.0417
[10 empty] | 11 | 12.65 | 2019-11-04 15:36 |  | 41 | 0 | 6 | 49.5458
[10 empty] | 12 | 13.8 | 2019-11-05 19:12 | 0 | 41 | 0 | 6 | 54.05
Sprint story:What? Why? For Who?
| No | Task | Asigned | Done | Verified | Presented
| 1 | Research context | x |  | na | na
| 2 | Terms & Accronyms | x |  | na | na
| 3 | Mindmap design |  |  |  | na
| 4 | Quotes (costs / times)
| 5 | Cost Analysis
| 6 | Risk Register
| 7 | Presentation
| 8 | Approval
| 9 | Task3
| 10 | Task4
| 11 | Task5
| 12 | Task6
| 13 | Task7
| 14 | QA
| 15 | Close-out
|  |  |  | (na) | 2 | 3 | Done | Todo | Progress
Totals |  | 13 | 2 | 0 | 0 | 0 | 2 | 47 | 4.255%
Formulas:
Days = DATEDIF([Start On:],[End on],"d")+1
Days left = DATEDIF([Start On:, row below],[End on],"d")
Adding tasks:
(More tasks can be added easily)
1. Insert spreadsheet lines
2. Drag table bigger
Sprint always has 12 status update events
Format Dates:
dd-mmm (hh:mm)
dd-mmm
Detail project planning:
1. All tasks need to be defined before start
2. Tasks need to be of equal duration
3. Scope shall be freezed upon project start
4. There shall be 12 status feedback update sessions
5. Two week period is the optimum duration
------------------------------------------------------
Advantages:
1. Provide sprint progress %
2. Give current task target to be done to complete within deadline
3. Burndown chart
4. Update of project status is simple and effective
5. This process has proven to be highly effective and productive specially with specific deadlines
Total Time to complete sprint:
- Contingency is subtracted from time
- Contigency of 2 days will exclude weekends
- Contigency of 0.1 days is about 2.4 hours / 24 hour day
(Real time is used -> 24 hour days & 7 days / week)
Note on X2: Days per week Default is 0.1 (2.4 hours per day or 17 hours per week)
Note on Y2: Duration factor is used to set the interval time for status updates for the sprint. (There is always 12 status updates)
Note on N4: See Duration Factor table
Note on O4: Add sprint start date
Note on C23: Every tasks has 4 stages before completion. Add "x" when task is completed.
Note on D23: Task is assigned to someone and has started
Note on E23: Task is reported to be completed
Note on F23: Task was verified by 2nd party. Mark with "x" if completed. Mark with "na" if task is not verified.
Note on G23: Task was presented to stakeholders. Mark with "x" if completed. Mark with "na" if task is not presented.
Note on F41: Verified "na" total
Note on G41: Presented "na" total
Note on C42: Total Tasks
Note on D42: Total assigned
Note on E42: Total done
Note on F42: Total verified
Note on G42: Total presented

## Sprint2
Copy Sprint 1 to this tab and update values to capture next sprint.